NIS Work Plan for the Ministry of Foreign Affairs

| Ministry of Foreign Affairs | Approved by: Ethics Committee date:12 March 2015 |
| --- | --- |
| Activities | Time frame January 2015 to June 2016 | Indicator | Unit/Person in charge |
|  |  | Baseline No. (as of Dec 2014) | Target No. | Unit |  |
| Institutional Arrangement |
| (1) Hold Ethics Committee Meeting | Quarterly | 3 | 4 | Number/year | Focal Point |
| (2) Formation of Ethics Committee in the subordinate offices, i.e. Foreign Service Academy, BIISS and all Bangladesh Missions abroad | By June’15 | 0 | 1+69+1 =71 | All subordinate offices | Chairman- BIISS, Principal- FSA and Heads of Mission |
| (3) Arrange the stakeholder meeting | By December’15 | 0 | 4 | Number of meetings/year | Focal Point |
| (4) Arrange the stakeholder meeting at all subordinate offices | By December’15 | 0 | (1+69+1)*4=284 | Number of meetings/year | Chairman- BIISS, Principal- FSA and Heads of Mission |
| 2. Awareness raising |
| (1) Hold awareness meeting at the Ministry Foreign Service Academy and all Bangladesh Missions abroad (1+1+69) | June 2016 | 0 | 4 | Number of meetings | Focal Point |
|  |  | 0 | 300 | Number of attendees | Focal Point |
| (2) Hold awareness meeting in the subordinate offices | June 2016 | 0 | 140 | Number of meetings | Principal, Foreign Service Academy and Heads of Mission |
|  |  | 0 | 1200 | Number of attendees |  |
| 3. Capacity Development |
| (1) Identify Key Performance Indicator for all | December 2015 | 0 | Set up KPI for all level of officers | Number of attendees | Focal Point |
| (2) Organize training on NIS at the Ministry | December 2015 | 0 | 75 | Number of attendees | Focal Point |
| (3) Provision of training on Right to Information (RTI) | December 2015 | 1 | 75 | Number attendees | Focal Point |
| (4) Organize of training on GRS | December 2015 | 0 | 75 | Number of attendees | Focal Point |
| (5) Provision of language training for the officers and staffs | December 2015 | 2 | 60 | Number of attendees | Focal Point |
| (6) Organize training on MRP, MRV and on consular and welfare services for the officers and staffs | December 2015 | 4 | 80 | Number of attendees | Focal Point |
| (7) Organize training on PPR for the officers | December 2015 | 1 | 25 | Number of attendees | Focal Point |
| Activities Time frame January2015 to June 2016 Indicator Unit/Person in charge Baseline No. (as of Dec 2014) Target No. Unit |
| (8) Organize training on Government tender procedure for the officers and staffs | December 2015 | 0 | 20 | Number of attendees | Focal Point |
| (9) Provision of training for Accounts management for the officers and staffs | December 2015 | 2 | 60 | Number of attendees | Focal Point |
| (10) Provision of training on etiquette of the staffs | December 2015 | 2 | 50 | Number of attendees | Focal Point |
| 4. Reforms and Formulation of Rules and Regulations |
| Completion of the translation (ongoing) of Foreign Service Rules in Bangla | June 2016 | 0 | 1 | Formulated | Administration Wing |
| Amendment of Bangladesh Foreign Service Rule | June 2016 | 0 | 1 | Formulated | Administration Wing |
| Completing the Formulation of proposed Ex Cadre recruitment rules | June 2016 | 0 | 1 | Formulated | Administration Wing |
| Formulation of Recruitment Rules for the 3rd class and 4th class employees of the Ministry | June 2016 | 0 | 1 | Formulated | Administration Wing |
| Formulation of Promotion Rules for the 4th class and 3rd class employees of the Ministry | June 2016 | 0 | 1 | Formulated | Administration Wing |
| Formulation of Local Staff Recruitment Rules for Bangladesh Missions abroad | June 2016 | 0 | 1 | Formulated | Administration Wing |
| Incorporate NIS as a module of training at Foreign Service Academy | June 2016 | 0 | 1 | Incorporated | Principal, Foreign Service Academy |
| Discussion with NIS focal points of other Ministries for further improvement | December 2015 | 0 | 5 |  | Focal Point |
| 5. Rewards for officers and officials |
| (1) Integrity award for best attitude officers and officials in the Ministry | June 2016 | 0 | 06 officers and 06 officials | Number of awards/ year | Foreign Secretary |
| (2) Foreign Training for best performing officers | July, 2015 | 0 | 05 | Number of awards/ year | Foreign Secretary |
| (3) Reward among the trainee officers for outstanding performance | December 2015 | 0 | 01 Trainee officer | Certificate & crest | Administration Wing |
| 6. NIS implementation |
| (1) Introducing new citizen charter for the Ministry | December 2015 | 0 | 1 | Citizen Charter | Administration Wing |
| (2) Introducing official e-mail use for all officers | July 2015 | 70% | 10% | Percentage of officers | Administration and ICT Wing |
| Activities Time frame January2015 to June 2016 Indicator Unit/Person in charge Baseline No. (as of Dec 2014) Target No. Unit |
| (3) Reducing the time lag to | December | 0 | 04 days | Days | Administration |
| provide consular service | 2015 |  |  |  | Wing |
| (4) Introducing Archive at the Ministry | December 2015 | 0 | 1 | Archive section | Administration Wing |
| 7. E-Governance |
| (1) Launching new web-site of the Ministry | June 2015 | 1 | 1 | Website | Director General (Administration & ICT) |
| (2) Introduction of intranet in the Head Quarters of the Ministry | July 2016 | - | 100% | Percentage of officers with intranet facility | Director General (Administration & ICT) |
| (3) Providing high speed internet connection in the Ministry | December 2015 | x | All 1st class officers | Coverage of PC with internet connectivity | Director General (Administration & ICT) |
| (4) Providing Wi-Fi connection throughout the Ministry | December 2015 | x | Wi-Fi connection every where | Provided | Director General (Administration & ICT) |
| (5) Introducing Consular Automation system in the Ministry | December 2015 | 0 | 100% | Percentage of consular services | Director General (Consular) |
| (6) Update the website on regular basis | June 2015 | x | Update all changes | x | DG(Administration & ICT) |
| (7) Introduction of Service portal | June 2015 | 0 | 1 | Portal | Director General (Administration) |
| (8) Introducing e-learning platform to provide e training | June 2016 | x |  | Introduced | Director General (Administration & ICT) |
| (9) Introducing E-procurement system | June 2016 | x |  | Introduced | Director General (Administration & ICT) |
| (10) Uploading tender/ invitation notices on | June 2016 | x | Upload 100% tender notice | Percentage | Director General (Administration & ICT) |
| (11) Introduction of Video Conference system | June 2016 | x | All missions | Number of missions | Director General (Administration & ICT) |
| (12) Automation of Central Library | June 2016 | x | Complete automation process | Automated | Director General (Administration & ICT) |
| (13) Introduction of e-filing | June 2016 | x | 3 Wings | Number of Wings | Foreign Secretary |
| 8. Transparency and Accountability |
| (1) Nomination & publication of GRS focal point | December 2015 | x | Target Achieved | Nominated & published | Administration Wing |
| Activities Time frame January2015 to June 2016 Indicator Unit/Person in charge Baseline No. (as of Dec 2014) Target No. Unit |
| (2) Nominating GRS focal points in all Bangladesh missions abroad | July 2015 | x | 69 | Number | Administration Wing |
| (3) Disposal of complaints | December 2015 | 15 | 25 | No. of Disposal | Legal Affairs Wing |
| (4) Informing the complaints about the result | December 2015 | - | 100% | Percentage of disposal | GRS focal point and EP Wing |
| (5) Uploading the report of GRS on the website | Monthly | - | 10th of each month | Date | GRS focal point and ICT Wing |
| (6) Sending GRS Report to Cabinet Division | Monthly (Dec. 2015) | - | 12 | No. per year | GRS focal point |
| (7) Introduction of online GRS System | June 2016 | - | - | Introduced | GRS focal point and ICT Wing |
| (8) Submission of wealth statement by the new recruited officer | July 2015 | - | 20 | No. of Submissions | Administration Wing |
| (9) Submission of wealth statement after each 5 years (all officers and staffs) | Dec, 2015 | - | 800 | No. of Submissions | Administration Wing |
| (10) Permission for buying & selling properties | Dec, 2015 | - | 100% | Percentage | Administration Wing |
| (11) Introduction of internal GRS one desk service | June, 2016 | - | - | Introduced | Administration Wing |
| 9. Innovation Team |
| (1) Ministry level meeting | Quarterly | - | 4 | meetings/year | Administrative Wing |
| 10. Right to Information |
| (1) Nomination of RTI focal point | - | - | Target achieved | Nominated | Administrative Wing |
| (2) Disposal of application for information | Dec, 2015 | - | 100% | Percentage | Administration Wing and External Publicity Wing |
| (3) Sending report on RTI to the Cabinet Division | Dec, 2015 | - | 04 | Number per year | RTI focal point and Administration Wing |
| 11. Internal Audit & Budget |
| (1) Introduction of Internal audit among the wings to maintain NIS | Dec, 2015 | - | 4 | Number of Wings per year | Director General (Administration) |
| (2) Introduction of Internal Mission audit by Inspector General of Mission | July 2015 | - | 06 | Number of Missions per year | Inspector General of Mission |
| (3) Arrange meeting for the | Dec, 2015 | - | 1 | Number per | Foreign Secretary |
| Activities Time frame January2015 to June 2016 Indicator Unit/Person in charge Baseline No. (as of Dec 2014) Target No. Unit |
| Consultation & Implementation of the suggestions proposed by the Internal audit |  |  |  | year |  |
| (4) Placement for Budget to the MoF for the NIS implementation | May, 2015 | - | - | Timely submission | Focal Point and Director (Finance) |
| 12. Monitoring |
| (1) Monitoring the implementation of the work plan | Dec, 2015 | - | 4 | Meetings/year | Ethics Committee |
| (2) Prepare monitoring report | Dec, 2015 | - | 4 | Number/ year | Focal Point and Research Wing |
| (3) Submit the annual report to the National NIS Committee | Dec, 2015 | - | 4 | Number/year | Focal Point |
| (4) Review this NIS Model Work Plan | Dec, 2015 | - | 1 | No. per year | Focal Point |