| **SDG targets** | **Global Indicators for SDG Targets** | **Lead/Co-lead Ministries/ Divisions** | **Associate Ministries/ Divisions** | **7th FYP Goals/Targets related to SDG Targets and Indicators** | **On-going Project/Programme to achieve 7th FYP Goals/ Targets** | **Requirements of New Project/ Programme up to 2020** | **Actions/ Projects beyond 7th FYP Period (2021-2030)** | **Policy/ Strategy if needed (in relation with Column 8)** | **Comments** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Project title and period** | **Cost in BDT (million)** | **Project title and period** | **Cost in BDT (million)** |
| **1** | **2** | **3** | **4** | **5** | **6.1** | **6.2** | **7.1** | **7.2** | **8** | **9** | **10** |
| Target 1.1 By 2030, eradicateextreme poverty for all people everywhere, currentlymeasured as people living on less than $1.25 a day | 1.1.1 Proportion of populationbelow the international poverty line, by sex, age, employmentstatus and geographical location(urban/rural) | **Lead:** CD (leading theNSSS);**Co-Lead:**GED (as NPFP) | BFID (BB); ERD; FD; LGD; MoA;MoCHTA; MoDMR; MoEWOE; MoF; SID MoFL; PMO;MoInd; MoLE; RDCD; MoLWA;MoSW;MoWCA;MoYS; | • The 7th FYP aims to reduce extreme poverty by about 4.0 percentage points to around 8.9% by FY20.• Replication of successful targeted livelihood programmes.• Support for human capital development for the extreme poor.Undertaking measures forpreventing and mitigating shocks• Further expansion of microcredit& micro savings• Expanded and inclusive socialprotection programmes for the extreme poor | Social Security Policy Support (SSPS) Programme | 453.49 | 1. Social Security Policy Support (SSPS) Programme-2nd phase. 2. Establishment of the integrated central GRS.3. Establishment of an Integrated Service Development Platform (ISDP) based on unique ID for each and every citizen | 1,000.00200.00500.00 | 1. Social Security Programme Consolidation Support (SSPCS).2. Management of the integrated central GRS.3. Management of the ISDP. | 1. National Strategy on GRS. |  |

| **SDG targets** | **Global Indicators for SDG Targets** | **Lead/Co-lead Ministries/ Divisions** | **Associate Ministries/ Divisions** | **7th FYP Goals/Targets related to SDG Targets and Indicators** | **On-going Project/Programme to achieve 7th FYP Goals/ Targets** | **Requirements of New Project/ Programme up to 2020** | **Actions/ Projects beyond 7th FYP Period (2021-2030)** | **Policy/ Strategy if needed (in relation with Column 8)** | **Comments** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Project title and period* | *Cost in BDT (million)* | *Project title and period* | *Cost in BDT (million)* |
| **1** | **2** | **3** | **4** | **5** | **6.1** | **6.2** | **7.1** | **7.2** | **8** | **9** | **10** |
| 1.2 By 2030, reduce at least by half the proportion of men,women and children of all ages living in poverty in all its dimensions according to national definitions | 1.2.1 Proportion of populationliving below the national poverty line, by sex and age | **Lead:** CD (leading theNSSS); **Co-Lead:**GED (as NPFP) | ERD; FD; LGD; MoA;MoCHTA; MoDMR;MoEWOE;MoF; MoFL; MoHFW;MoInd; SID MoLE; PMO; MoRA; MoSW;MoWCA;MoYS; RDCD | •The 7th Plan seeks to reducepoverty rate to 18.6% by FY20•Creating good jobs for the largepool of under-employed and new labour force entrants by increasing the share ofemployment in the manufacturing sector from 1 5percent to 20 percent•Enhanced focus on foodproductivity and food security•Emphasis on agriculturaldiversification• Efforts concentrating on labourintensive manufacturing with focus on export diversification•Emphasis to formal servicesincluding exports of non-factor services (tourism,shipping andICT)• Emphasis on worker serviceexports in order toincrease theinflow of remittances withefforts to expand theopportunities to less served areas | Social Security Policy Support (SSPS) Program | 453.49 | 1. Social Security Policy Support (SSPS) Programme-2nd phase. 2. Establishment of the integrated central GRS.3. Establishment of an Integrated Service Development Platform (ISDP) based on unique ID for each and every citizen | 1000.00200.00500.00 | 1. Social Security Programme Consolidation Support (SSPCS).2. Management of the integrated central GRS.3. Management of the ISDP. | 1. National Strategy on GRS. |  |
| 1.2.2 Proportion of men,women and children of all agesliving in poverty in all itsdimensions according to national definitions | **Lead:** CD (leading theNSSS); **Co-Lead:**GED (as NPFP) | ERD; LGD; MoA; PMO;MoCHTA;MoDMR;MoEWOE;MoF; MoFL;MoHFW;MoInd; SID MoLE; FD; MoRA; MoSW;MoWCA;MoYS; RDCD; |

| **SDG targets** | **Global Indicators for SDG Targets** | **Lead/Co-lead Ministries/ Divisions** | **Associate Ministries/ Divisions** | **7th FYP Goals/Targets related to SDG Targets and Indicators** | **On-going Project/Programme to achieve 7th FYP Goals/ Targets** | **Requirements of New Project/ Programme up to 2020** | **Actions/ Projects beyond 7th FYP Period (2021-2030)** | **Policy/ Strategy if needed (in relation with Column 8)** | **Comments** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| *Project title and period* | *Cost in BDT (million)* | *Project title and period* | *Cost in BDT (million)* |
| **1** | **2** | **3** | **4** | **5** | **6.1** | **6.2** | **7.1** | **7.2** | **8** | **9** | **10** |
| 1.4 By 2030, ensure that all men and women, in particularthe poor and the vulnerable,have equal rights to economicresources, as well as access tobasic services, ownership and control over land and otherforms of property,inheritance, natural resources,appropriate new technologyand financial services, including microfinance |  1.4.1 Proportion of populationLiving in households with access to basic service | **Lead:** CD (leading theNSSS); **Co-Lead:**RDCD | BFID (BB); FD; ICTD; LGD; LJD; LPAD; MoA;MoCHTA;MoEF; MoL;MoEWOE;MoFL; SID MoInd;MoLWA;MoWCA;MoWR; MoYS; | Special attention to further closing the gap between the rich and the poor in accessing basicservices with special focus on the bottom 20 percent where the gap is the highest | Social Security Policy Support (SSPS) Programme | 453.49 | 1. Social Security Policy Support (SSPS) Programme-2nd phase. 2. Establishment of the integrated central GRS.3. Establishment of an Integrated Service Development Platform (ISDP) based on unique ID for each and every citizen | 1000.00200.00500.00 | 1. Social Security Programme Consolidation Support (SSPCS).2. Management of the integrated central GRS.3. Management of the ISDP. | 1. National Strategy on GRS. |  |
| 1.4.2 Proportion of total adult population with secure tenure rights to land, with legally recognized documentation and who perceive their rights to land as secure, by sex and by type of tenure  |
|  |